## Bug Report
Bug reports
ID | Issue Type | Issue Title | Steps | Expected Result | Actual Result | Evidence | Video
Component: CHECKOUT PAGE
Bug-01 | Functional | Proceed to billing button is not enabled preventing the client to finish the purchase | 1) Enter the website https://qatest-dev.indvp.com/ with a logged user 2) Add product to Cart https://qatest-dev.indvp.com/product/alvarado-tray 3) Open the Mini Cart on the top right corner (via header) and click on SECURE CHECKOUT button from the overlay 4) Click on PROCEED TO BILLING button in the lower left corner of the Checkout page NOTE even using different custom adresses the button is not enabled | Proceed to billing button is clickable and leads to the Billing Form to complete the purchase | Proceed to billing button is not clickable/enabled. Purchase cannot be completed | https://app.screencast.com/t2ExzmbHbHBcs | https://watch.screencastify.com/v/piGUATqeze6HTbbpydJO
Component: CART
Bug-02 | Functional | Discount product price is not applied on final order in the mini CART overlay | 1) Enter the website https://qatest-dev.indvp.com/ with a logged user 2) Add Product To Cart https://qatest-dev.indvp.com/product/ananda-brass-nested-bowls-set-of-three 2) Open the Mini Cart on the top right corner (via header) and check the price of the added product | The product discount shown in the PDP is deducted from the final order shown in the mini CART overlay | The product discount is not applied in the final order shown in the mini CART overlay | https://app.screencast.com/8BGqRgmrs8RX8
Component: HOMEPAGE
Bug-03 | Visual | "Sophie Conran" logotype is missing from the Home page header | Open home page to see the missing logotype | When opening the home page, the logotype is displayed in the header | No logotype is displayed in the header of the website | https://app.screencast.com/EnFXyx0hsKc2G
Bug-04 | Content | Missing content in Trade Enquiries footer link | Open Trade Enquiries page from the website footer links | Page should display the trade enquiries content in the CMS | Missing content, where it is expected to be | https://app.screencast.com/llna2sjX3uCOF
Bug-05 | Functional | "404 error" is displayed when clicking on CONTACT US footer link | 1) Open Home page https://qatest-dev.indvp.com/ 2) Open Contact Us footer link | Contact Us Page opens and shows the contact form | "404 error page" is displayed. See screenshot | https://app.screencast.com/pDJvIkoyR7OnK
Bug-06 | Functional | "Internal server error" message is displayed when clicking SEND CATALOGUE REQUEST footer link | 1) Open Home page https://qatest-dev.indvp.com/ 2) Open Catalogue Request footer link 3) Complete the Catalogue Request Form with the validated information of the logged user 4) Click on SEND CATALOGUE REQUEST button at the bottom of the form | The message "Request successfully sent" is displayed on the screen. | "Internal server error" message is displayed on the screen. See screenshot | https://app.screencast.com/Jb5QzrHfE5wrc
Bug-07 | Functional | Header button to create new account displays a sign in form | 1) Open Home page https://qatest-dev.indvp.com/ 2) Click on Create an Account button on the top right corner (via header) | "Create new account" form opens and shows the fields of Personal and Sign-up information to complete | "Sign in to your account" form opens and shows the Login and Password fields to complete | https://app.screencast.com/kdNykS9WTARrG
Bug-08 | Content | Link name in the main menu is not translated into English | Open Home Page to see the text not translated in the main menu | Link should be "HOME DECOR" | Link says "HOME DÉCOR" with a tilde symbol | https://app.screencast.com/CjfQPP6u6GFd4
Bug-09 | Perfomance | Total load of the webpage in incognito mode takes more than 3 seconds | 1) Open home page https://qatest-dev.indvp.com/ in the Google Chrome browser in incognito mode 2) Open Dev Chrome Tools and check the total load time and thick the "disable cache" checkbox | The page load should take less than 3 seconds to completely load | Total load of the page in incognito mode takes 7.42 seconds. See video |  | https://watch.screencastify.com/v/lP2db9H0oU5O5bBmC5Mb
Bug-10 | Functional | Predictive autocomplete or suggestive search method in search bar not working | 1) Open Home page https://qatest-dev.indvp.com/ 2) Click on input field from the search bar and write the product name | Search bar displays a dropdown list of suggestions that changes as the user adds characters to the search input | Search bar displays a graying menu without showing suggestions when writing the complete product name | https://app.screencast.com/JvbM8LHu5Vt4H | https://watch.screencastify.com/v/3FCg4hMZOLBTUBqMuGsD
Bug-11 | Perfomance | Total load of the webpage in simulated mobile device takes more than 3 seconds | 1) Open home page https://qatest-dev.indvp.com/ in the Google Chrome browser in incognito mode 2) Open Dev Chrome Tools and thick the "disable cache" checkbox in Network tab. 3) Select 4x CPU Slowdown option in Perfomance tab 4) Select "mobile" device and "Perfomance" category in Lighthouse tab 5) Click on Analyze page load button | The page load should take less than 3 seconds to completely load | Total load of the page in incognito mode takes 9 seconds. See video |  | https://watch.screencastify.com/v/RsxnBhvHtCs9wBJfPOPv
Bug-12 | Functional | "404 error" is displayed when clicking on SALE ROOM button in the main menu | 1) Open home page https://qatest-dev.indvp.com/ 2) Click on SALE ROOM menu overlay item | Sale Room Page opens and shows the content | "404 error page" is displayed See screenshot | https://app.screencast.com/zcoGVIV75Ar39
Component: PRODUCT LIST PAGE
Bug-13 | Crossbrowser | Breadcrumb list from product listing page stops working on Edge and Safari browser | 1) Open home page on Edge browser (v 112.0.1722.48) and Safari browser (15.6.1 -17613.3.9.1.16) 2) Click on NEW IN dropdown button on main menu 3) Select a product form the list (https://qatest-dev.indvp.com/azure-hand-blown-glass-collection) and browse back to New in from the breadcrumb list | Breadcrumb list displays the location of the current page allowing the customer to browse back to product listing page | Breadcrumb list stops working, there is a gray line. See screenshot | https://app.screencast.com/x3gW0sLCznARr
Bug-14 | Crossbrowser | Dropdown list of KITCHEN & DINING link remains displayed when the cursor is not over the link in Safari browser | 1) Open home page on Safari browser (15.6.1 -17613.3.9.1.16). 2) Open ALL KITCHEN & DINING product list page https://qatest-dev.indvp.com/kitchen-dining 3)Move the cursor on KITCHEN & DINING menu link and then move the cursor out of the link See video | Dropdown list of the KITCHEN & DINING link disappears when the cursor is moved out of the link | Dropdown list of KITCHEN & DINING link remains displayed when the cursor is moved out of the link |  | https://app.screencast.com/HXg2eRCjuFLqK
Bug-15 | Crossdevice | "404 error page" and error message are displayed when opening product listing pages from dropdown menu on tablet device | Open home page on Ipad Pro 12.9 (Safari browser v 14.0) and click on Mugs & Cups link from the KITCHEN & DINING dropdown menu | Mugs & Cups Page opens and shows the list of all Products/Items. | "404 error page" and "Error fetching product list" message are displayed. See video | https://app.screencast.com/Hj3rXnz5mhlNX | https://watch.screencastify.com/v/NdmyNoskh3woPOXrS6Nj
Bug-16 | Functional | "404 error" is displayed when open Product image gallery page | 1) Open home page https://qatest-dev.indvp.com/ 2) Click on GIFTS dropdown menu at the main menu bar 3) Select WEDDING GIFTS from the dropdown menu | Wedding Gifts Products Page opens and shows the list of all Products/Items. | "404 error page" is displayed with an "Error fetching product list" message at the right side See screenshot | https://app.screencast.com/9PfhEFWHqH7dQ
Component: PRODUCT DESCRIPTION PAGE
Bug-17 | Functional | "Out of stock" message appears when adding an available stock product and ADD TO BASKET button crashes after clicking | 1) Enter the website https://qatest-dev.indvp.com/ with a logged user 2) Add one item of each child product to Cart https://qatest-dev.indvp.com/azure-hand-blown-glass-collection 3) Click on ADD TO BASKET button located under the product description | The message "Product added to the cart" is displayed on the screen and the product is succesfully added to the shopping cart. | Three messages "Product that you are trying to add is not available" are displayed on the screen and no product is added to the cart. In addition the ADD TO BASKET button freezes in ADDING... state | https://app.screencast.com/tFUgr9rcdNqyn
Bug-18 | Functional | Out of stock product can be added to the shopping cart | 1) Enter the website https://qatest-dev.indvp.com/ with a logged user 2) Add one item of each child product to Cart https://qatest-dev.indvp.com/cornflower-tree-of-life-bed-linen-collection 3) Click on ADD TO BASKET button located under the product description | The message "Sorry! The product is out of stock!" is displayed on the screen and no product is added to the cart | The message "Product added to the cart" is displayed on the screen and the product is succesfully added to the shopping cart. | https://app.screencast.com/TSNhWV83N7OhD
Bug-19 | Functional | Breadcrumb list does not match the current location of the product page | 1) Open home page https://qatest-dev.indvp.com/ 2) Click on HOME DÉCOR dropdown menu in the main menu bar 3) Select ALL HOME DÉCOR from the dropdown menu 4) Click on product link https://qatest-dev.indvp.com/alvarado-tray | Breadcrumb list displays the location of the current page allowing the customer to browse back to the ALL HOME DÉCOR product listing page | Breadcrumb list displays a different location of the current page | https://app.screencast.com/ea9Y4HIs9kCyt
Component: CMS
Bug-20 | Crossdevice | Change of font size in the content text of the Privacy Policies page on android mobile device | Open home page on Android phone 8.1.0 (Chrome browser v112.0) and open Privacy Policies footer link | Title font size of the Privacy Policies page content maintain the page layout on android phone screen | Title font size of the Privacy Policies page are smaller than the original page layout | https://app.screencast.com/8r0SCDdUWtfVn
Bug-21 | Visual | Missing image in content button when screen size is changed | Open home page, to see the issue in dynamics, decrease page width (to breakpoints between 767 x 1176 pixels) and see how "Image not found" text appears in SHOP CUTTLERY content link. | Content button should adapt to screen size change. | "Image not found" text appears in the SHOP CUTTLERY content link | https://app.screencast.com/3FwzcAUrDpSYt